## Cover
TEST PLAN
Project Name | ShopeeTesting |  |  | Reviewer | Trần Thị Thanh Nga
Project Code | ST |  |  | Review date | 30/10/2024
Creator | Nguyễn Hoàng Ánh Dương/Nguyễn Thị Chúc Ngân/ Huỳnh Ngọc Quang Minh/Lại Thị Bích Phượng/ Lê Nguyễn Hoàng Nam |  |  | Approver | Trần Thị Thanh Nga
Version | v1.0 |  |  | Approval Date | 31/10/2024
Record of change
Effective Date | Version | Change Item | A, D, M | Change description
26/10/2024 | v1.0 | Initial
Index
Sheet Name | Description |  |  |  | Note
Cover | Title page
Test Policy | General policy for Test process, Test case design, Test Data List of requirements to Test/not Test Exit criteria for testing Suspension criteria and Resumption requirements
Test Management | Test scope Deliverable Management method Risk Assumption Training plan
Test Strategy | Identification of Test level, Test types, Test environments, Test data and Enviroment for test
Master Schedule | Introduction and Define team, master schedule for testing
Appendix | Description and detailed definition of Test level, types and techniques List of Terminologies and definition/explanation |  |  |  | For Reference only
Reference Document
Name |  |  |  | Version | Note
Shoppee SRS |  |  |  | 0.5
Note on E10: ====== ID#AAAAHNbKGmo (2020-11-08 05:44:12) - A: Added - D: Deleted - M: Modified

## Test Policy
Test Policy
Test process policy
Description of policies of testing process.
| # | Description | Responsibility | Note
1
2
Test case design policy
Description of policies of test case design.
| # | Items | Note
1
2
Quality metric
Description of target
| # | Items | Target | Note
Pass/Fail Criteria
The conditions that the testing must satisfy to end test.
| # | Criteria | Priority | Note
| 1 | 80% of completed test cases / total test cases (test coverage > 80%) |  | Carry out test cases with highest priority first, then increase gradually.
| 2 | Test successful coverage >= 80%
| 3 | Software is correct with SRS
Suspension Criteria and Resumption Requirements
Specify when to pause in a series of tests and requirements for resumption of test activities.
| # | Suspension Criteria | Note
| 1 | When a defect is introduced that cannot allow any further testing
| 2 | A specific holiday shuts down both development and testing (Tet Holiday)
| 3 | If there is any network, hardware problem in the organisation, we can suspend testing
| 4 | If we got more pending requests with the development team
| # | Resumption Requirements | Note
| 1 | When the particular issue has been addressed and solved

## Test Management
Test Management
Test Scope
Listing of test items in test process.
# | Items |  | Description |  | Responsibility | Note
1 | Create test plan |  |  |  | Leader / Testers
2 | Create test design |  |  |  | Tester
3 | Create test cases |  |  |  | Tester
4 | Create test data |  |  |  | Teseter
5 | Execute system test |  |  |  | Teseter
6 | Defects list |  |  |  | Teseter
7 | Create test report |  |  |  | Leader / Testers
Deliverables
Listing of documents will be delivered of test process.
# | Deliverables |  | Delivered date | Delivered by | Delivered to | Note
1 | Test plan |  | 26/10/2024 | Test leader | Test manager, Team | This document itself
2 | Test cases |  | 26/10/2024 | Test leader | Test manager, Team
3 | Defect logs |  | 26/10/2024 | Test leader | Test manager, Team
4 | Test report |  | 26/10/2024 | Test leader | Test manager, Team
Management method
Describe the management method of test process.
# | Object |  | Method |  |  | Note
1
2
3
Risks
Listing of all risks of test process and action to mitigate the risk and do if risk become reality.
# | Condition |  |  | Mitigation |  | Contingency
1 | Team members lack experience in software testing domain |  |  | Plan training course to skill up your members |  | 1. Connect with a training organization 2. Attend mandatory training 3. Quality test
2 | The development team improved the code which led to the testing process being paused |  |  | Accept this risk |  | Contact the development team
3 | The project schedule is too tight; it's hard to complete this project on time |  |  | Set test priority for each test case and execute the test case with the highest priority |  | 1. Determine the priority for each test case 2. Set priority for each test case 3. Follow the priority level
4 | Members misunderstood the request |  |  | Organize to review and analyze requirements to member before starting the testing process |  | 1. Hold a meeting 2. Review required 3. Inspections
5 | Employees reduce working performance after Tet holiday |  |  | Accept this risk |  | OT to keep up with the schedule
Assumption
Listing of all assumption of test process.
# | Type |  | Description
1
2
Training Plan
Plan training for test team.
# | Training Topic |  | Description |  | Responsibility | Start Date | End Date
1
2
3
Note on F31: ====== ID#AAAAHNbKGmc (2020-11-08 05:44:12) steps keep a risk from occurring or driving its impact to an acceptance level
Note on H31: ====== ID#AAAAHNbKGmk (2020-11-08 05:44:12) steps would have to be done if the risk were to become reality
Note on C40: ====== ID#AAAAHNbKGmY It can be (2020-11-08 05:44:12) - Requirement - Test Products - Test environment - Test tools ...

## Test Strategy
Test Strategy
Test Objective:
To ensure doesn’t contain serious bugs before release to customer, to confirm that the system has met the requirements
Test stages & techniques
Listing of all test stages of project, and test techniques must be done of every test stages.
Test stage | Unit testing | Integration Testing | System Testing | User acceptance testing
Test techniques
White box testing | x |  | x
Black box testing |  | x | x | x
Responsibility | Developer | Tester | Tester | Tester
Listing of what is to be tested from the USERS viewpoint of what the system does.
Feature/Function |  | Document which is testing base on |  |  | Note
Các tính năng chính của Shoppee được mô tả ở tài liệu SRS được thực hiện test theo độ ưu tiên từ cao đến thấp (Cao thực hiện trước và thấp thực hiện test sau). |  | Shopee_SRS-V1
Test environment
Listing of environments use in test process.
Type | Environment |  |  |  | Note
Hardware | Laptop, |  |  |  | Standard Fsoft
OS | Window 11 64bit
Software | Chrome
Database | MS SQL
Browser | Chrome
Network configured | LAN Wifi
Note on G10: ====== ID#AAAAHNbKGmg (2020-11-08 05:44:12) - manual - test tool …

## Master Schedule
Master Schedule
Project Team
Listing of all workers join the testing process
| # | Worker / Doer | Position | Responsibilities
| 1 | 21130328-Nguyễn Hoàng Ánh Dương | Leader | Read and Analyze Doccument, test design, test case, thực thi các test case, logs bug cho chức năng Thanh toán
| 2 | 21130451-Nguyễn Thị Chúc Ngân | Member | Read and Analyze Doccument, test design, test case, thực thi các test case, logs bug cho chức năng Quy trình đặt hàng
| 3 | 21130488-Lại Thị Bích Phương | Member | Read and Analyze Doccument, test design, test case, thực thi các test case, logs bug cho chức năng Tìm kiếm
| 4 | 21130445-Huỳnh Ngọc Quang Minh | Leader | Read and Analyze Doccument, test design, test case, thực thi các test case, logs bug cho chức năng Quản lí sản phẩm
| 5 | 21130112-Lê Nguyễn Hoàng Nam | Member | Read and Analyze Doccument, test design, test case, thực thi các test case, logs bug cho chức năng Theo dõi đơn hàng
Master Schedule
# | Item | Start Date | End Date
1 | Create test plan | 2024-10-26 | 2024-10-28
2 | Create test design | 2024-10-29 | 2024-11-01
3 | Create test case | 2024-11-02 | 2024-11-08
4 | Execute test and log bugs | 2024-11-09 | 2024-11-15
5 | Evaluting exit criteria & Test report | 2024-11-16 | 2024-11-22
6 | Review | 2024-11-23 | 2024-11-29
| Task | Start day from 26/10/2024 | Duration
| Create test plan | 0 | 2
| Create test design | 2 | 3
| Create test case | 5 | 6
| Execute test and log bugs | 11 | 6
| Evaluting exit criteria & Test report | 17 | 6
| Review | 23 | 7

## Detail Schedule
# | Item | Responsibilities | October | [5 empty] | November
|  |  | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | Create test plan | Team | bar: October 26 to October 28
2 | Create test design | bar: October 29 to November 1
2.1 | Quy trình thanh toán | 21130328-Nguyễn Hoàng Ánh Dương | bar: October 29 to October 31
2.2 | Quy trình đặt hàng | 21130451-Nguyễn Thị Chúc Ngân | bar: October 29 to October 31
2.3 | Chức năng tìm kiếm sản phẩm | 21130488-Lại Thị Bích Phương | bar: October 29 to October 31
2.4 | Quản lý sản phẩm | 21130445-Huỳnh Ngọc Quang Minh | bar: October 29 to October 31
2.5 | Theo dõi đơn hàng | 21130112-Lê Nguyễn Hoàng Nam | bar: October 29 to October 31
2.6 | Review | Team | bar: November 1

## Appendix
Appendix
Term definition
# | Term | Definition/explanation
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
17
Glossary
#
1
1
2
3
4
#
4
5
6
7
8
9
10
11
12
13
14
Members
1 | 21130328-Nguyễn Hoàng Ánh Dương
2 | 21130451-Nguyễn Thị Chúc Ngân
3 | 21130488-Lại Thị Bích Phương
4 | 21130445-Huỳnh Ngọc Quang Minh
5 | 21130112-Lê Nguyễn Hoàng Nam